## Slide 1: NARVAL-II Preparation Workshop Schedule
Katrin Witte
May 12, 2016
Cologne

## Slide 2: HALO Timetable

## Slide 3: NARVAL-II
NARVAL-II | 
Number of Flights | 12,5*
Number of Flight Hours | 95
Period for instrument integration | 7 weeks
Period for Mission | 3,5 weeks
Ferry Oberpfaffenhofen – Barbados | Mon, Aug 08
Ferry Barbados – Oberpfaffenhofen | Wed, Aug 31
Period for instrument de-installation | 1 week
* Costs for EMI-Flight will be splitted between NARVAL-II and NAWDEX
DLR.de • Chart 3

## Slide 4: NARVAL-II
12,5 Flights total for NARVAL-II |  | 
Flights | 0,5 | EMI-Flight
 | 0 | Scientific Test Flight
 | 2 | Ferry-/Transfer-Flights
 | 10 | Mission Flights from Barbados
95 Flight Hours total for NARVAL-II |  | 
Flight Hours | 1,5 | EMI-Flight
 | 0 | Scientific Test Flights
 | 24 | Ferry-/Transfer-Flights
 | 69,5 | Mission Flights

## Slide 5: Important Certification Milestones
Certification Milestones |  | 
Wed | Feb 03, 2016 | Delivery of Preliminary Interface Control Documents
Wed | Feb 17, 2016 | Preliminary Design Review
Wed | Mar 16, 2016 | Delivery of Final Interface Control Documents
Wed | May 04, 2017 | Critical Design Review Design Go/No-Go for specMACS

## Slide 6: Schedule for Instrument installation
Installation will start with installing equipment underneath the floor/back of the aircraft (Boiler Room)
Continue with the instruments in the back of the aircraft
Continue installing instruments towards the front of the aircraft
Typical working hours at the aircraft in the hangar (Oberpfaffenhofen):
Monday – Friday 08:00 – 17:00
On weekends in Oberpfaffenhofen: currently no work inside the hangar planned for the weekends in Oberpfaffenhofen
Access to the offices possible during weekends in Oberpfaffenhofen

## Slide 7: Cabin Layout
Seat for DLR´s technician
6 scientists can be on board!

## Slide 8: Mountings on the Fuselage
Cooling Device
HAMP
specMACS
14 Belly Pod Fenster
13 Fenster für View Ports
10 Belly Pod Sektion A für NARVAL
19 HAMP (Radiometer)
21 TGI-430

## Slide 9: Schedule Installation (1)
Week 25 | Mon | 20.06.2016 | Integration | Fiber optic cables for specMACS, De-installation of seats, specMACS
 | Tue | 21.06.2016 | Integration | SMART-Sensors on Apertures, Dropsonde rack/dispenser, SMART-Rack, seats
 | Wed | 22.06.2016 | Integration | Belly Pod-Frame, Feed-through HAMP-Apertures, HAMP-Racks, Ventral Fin
 | Thu | 23.06.2016 | Integration | HAMP-Radar antenna, Radiometer, TGI-430, SHARC
 | Fri | 24.06.2016 | Integration | Cooling Device on Viewport (Kühlflansch) / WALES
 | Sat | 25.06.2016 |  | 
 | Sun | 26.06.2016 |  | 
Week 26 | Mon | 27.06.2016 | Integration | WALES
 | Tue | 28.06.2016 | Integration | WALES
 | Wed | 29.06.2016 | Integration | Buffer for integration of instruments
 | Thu | 30.06.2016 |  | DLR´s annual works outing
 | Fri | 01.07.2016 | Integration | Buffer for integration of instruments
 | Sat | 02.07.2016 |  | 
 | Sun | 03.07.2016 |  | 

## Slide 10: Schedule Installation (2)
Week 27 | Mon | 04.07.2016 | mech./elect. Acceptance | specMACS, HALO-SMART
 | Tue | 05.07.2016 | mech./elect. Acceptance | HAMP, SHARC/TGI-430
 | Wed | 06.07.2016 | mech./elect. Acceptance | WALES
 | Thu | 07.07.2016 | mech./elect. Acceptance | Buffer for mech./electrical Acceptance
 | Fri | 08.07.2016 | mech./elect. Acceptance | Buffer for mech./electrical Acceptance
 | Sat | 09.07.2016 |  | 
 | Sun | 10.07.2016 |  | 
Week 28 | Mon | 11.07.2016 | Preparation | EMI-Ground Test
 | Tue | 12.07.2016 | Realization | EMI-Ground Test
 | Wed | 13.07.2016 | Buffer | Buffer for EMI-Ground Test
 | Thu | 14.07.2016 | Troubleshooting | 
 | Fri | 15.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Sat | 16.07.2016 |  | 
 | Sun | 17.07.2016 |  | 

## Slide 11: Schedule Installation (3)
Week 29 | Mon | 18.07.2016 | Preparation | EMI-Flight
 | Tue | 19.07.2016 | Realization | EMI-Flight
 | Wed | 20.07.2016 | Buffer | Buffer for EMI-Flight
 | Thu | 21.07.2016 | Buffer | Buffer for EMI-Flight
 | Fri | 22.07.2016 | Buffer | Buffer for EMI-Flight
 | Sat | 23.07.2016 |  | 
 | Sun | 24.07.2016 |  | 
Week 30 | Mon | 25.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Tue | 26.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Wed | 27.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Thu | 28.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Fri | 29.07.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Sat | 30.07.2016 |  | 
 | Sun | 31.07.2016 |  | 
Week 31 | Mon | 01.08.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Tue | 02.08.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Wed | 03.08.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Thu | 04.08.2016 | Functional Tests | Scientific/Functional Tests on ground
 | Fri | 05.08.2016 | Preparation | Preparation for Ferry
 | Sat | 06.08.2016 |  | 
 | Sun | 07.08.2016 |  | 

## Slide 12: De-Installation of instruments after NAWDEX
2 week intermission between NARVAL-II & NAWDEX:
no scheduled deinstallation/maintenance of instruments
Tue, Oct 18, 2016: Ferry Keflavik – Oberpfaffenhofen
Wed, Oct 19, 2016: Customs, Beginn of deinstallation WALES
Thu, Oct 20, 2016: De-installation WALES, Belly Pod/Ventral Fin
Fri, Oct 21, 2016: HAMP, Radar antenna, radiometer, seats
Mon, Oct 24, 2016: TGI-430, SHARC, SMART, specMACS
Tue, Oct 25, 2016: Buffer

## Slide 13: Access Badges for DLR
In order to receive long-term access badges for DLR, we need some information:
  Name, Institute, Adress, Telephone, Mail. Birthday, Birthplace, Nationality
  Confirmation from your Institute/Company
List should be provided to DLR until May 17, 2016
With these access badges, you don´t need to pick-up and return your badge every morning/evening.
Access Badges will be valid from beginning of installation (June 20) until the end of de-installation period (Oct 25)

## Slide 14: Administrative Schedule
Current contractual status: Pre-Study („Vorstudie“) until June 19, 2016
  Costs for installation/deinstallation splitted between NARVAL-II & NAWDEX
With the beginning of the installation: Mission contract („Missionsvertrag“) for
  NARVAL-II
  NAWDEX
must be signed
DFG-Approvals won´t be sent prior to July 05, 2016
  Work-around via Dispense Letter from DFG planned
  Feedback from DFG-partner´s administrations and University of Leipzig needed until May 20

## Slide 15: Thank you!
HALO-Website: http://www.halo.dlr.de